## Sheet1
Stage | Tasks | Comments | Who is Responsible
Pre-Contract Activities | Deal Sourcing (brokers/direct seller relationship/other avenues)
Underwrite the deal (R/L review, rent comps, rehab estimate)
Submit LOI
Negotiate the deal
Get deal under contract
Manage the transaction (start to close)
Initial deposit (earnest money)
Due Diligence | Inspect the units (walk all units)
(Pre and Post Contract) | Review financial documents (P/L, rent roll, existing contracts (laundry, office equipment etc)
Lease/rent roll audit
Rent comps and competition shopping
Estimate rehab costs
Get bids for repair (rehab, contacts (laundry, office equipment, cable, trash)
Document the unit inspection process (Standardize the checklist)
Stop/retrade/move forward (based on contract)
Additional deposit (may have additional deposits to extend contract)
Insurance bids
Estimate tax increases
Interview/decide on PM
Bring on additional GP partners (equity etc)
Bring in a Fund to Fund partner?
Legal | Deal structure (Returns/splits etc)
Identify and engage SEC attorney
Identify and engage LLC attorney (if different from SEC attorney)
Review and approve PPM
Review approve LLC
Review and approve Subscription Agreement
Ensure SEC paperwork has been filed
Capital Raising | Create Investment Summary
Webinar
Investor meetings
Investor portal administration (Configure Portal and load the deal, support the users)
Get PPM signed
Keep track of capital raising progress (are the goals being met)
Keep track of incoming wires
Designate someone to manage the capital raise process
Explore Cost Segration benefits
Financials | Identify lender
Complete loan application
Additional at risk funds (inspections, studies, lawyer, tax abatement consultant, travel)
Loan guarantor (Balance sheet, sign on loan)
Experience
Liquidity (10% of loan amount, post close). Combination of funds
Net worth of team must equal loan amount.
Manage the refinance process (If a refi happens at some point)
Any Equity Investor investing more than 10-20% depending on lender will need to be KP
Pre-Closing | Create a plan for property takeover (What should happen on day 1?)
Having vendors ready (rebanding, painting etc)
Closing | Ensure lender is ready to close
Ensure equity capital is available
Actual closing (sign all the documents)
Taking over management and start to implement the business plan
Asset Management | Execute the business plan
Solicit rehab bids
Managing the construction/renovation (Project management)
Property management meetings/calls (Weekly/monthly)
Site visits/audits
Managing finances (OpEx and CapEx expense management) Review bills, ensure on-time payment of all expenses
IT resources (PM SW, Investor portal, Slack, Asana etc)
Monthly GP calls
Investor communication (monthly/quarterly)
Investor/GP distribution
Tax returns
Loading K1 to investor portal
Disposition | Contract with broker to list the property
Review offers
Decide on who's offer to accept
Close the sale
Distribute proceeds to LPs/GPs